## Sprint 1 - Work Log
Dates | Member | Start Time | End Time | Time Spent | Description
2026-01-23 | Ethan Elkaim | 0.79167 | 0.85417 | 0.0625 | Set up skeleton for app including resuable nav bar and home page + base css for app layout and nave bar
2026-01-24 | Martin Miskovski | 0.875 | 0.97917 | 0.10417 | Started the Registeration UI, Set up a CSS, EJS, JS
2026-01-24 | Marc Urbano | 0.875 | 0.9375 | 0.0625 | Set up Login.ejs, started HTML for login UI. Configured contrainer for reqiured fields.
2026-01-25 | Ethan Elkaim | 0.58333 | 0.64583 | 0.0625 | Set up server.js routes so the pages load + Started client side verification for registration
2026-01-26 | Martin Miskovski | 0.79167 | 0.83333 | 0.041667 | Designed the layout of the page, added html logic to properly save user inputs
2026-01-27 | Ethan Elkaim | 0.79167 | 0.83333 | 0.041667 | Finished client side verification for registration
2026-01-27 | Kadio Paul-Philippe Ehui | 0.79167 | 0.875 | 0.083333 | Set up the Login back- end implementation by adapting the front.
2026-01-27 | Martin Miskovski | 0.83333 | 0.91667 | 0.083333 | Worked on the css,
2026-01-28 | Kepler Paul-Emile | 0.79167 | 0.875 | 0.083333 | Started organizing the profile management page:html, containers ,button ,select elements
2026-01-29 | Ethan Elkaim | 0.875 | 0.91667 | 0.041667 | Started server side verification for registration
2026-01-30 | Ethan Elkaim | 0.79167 | 0.83333 | 0.041667 | Finished setting up server side verification for registration page
2026-01-30 | Chrisjan Alejandro | 0.79167 | 0.875 | 0.083333 | Started backend logic for saving user preferences. Created initial JSON structure for storing allergy and diet data.
2026-01-30 | Marc Urbano | 0.58333 | 0.66667 | 0.083333 | Completed Login UI skeleton, added login.css for login UI styling.
2026-01-31 | Chrisjan Alejandro | 0.79167 | 0.83333 | 0.041667 | Implemented server-side validation for incoming preference data to ensure correct format before saving.
2026-02-01 | Ethan Elkaim | 0.875 | 0.91667 | 0.041667 | Tested server side verification and fixed a few bugs + css
2026-02-01 | Kadio Paul-Philippe Ehui | 0.64583 | 0.72917 | 0.083333 | Improving the backend logic with session.
2026-02-01 | Kepler Paul-Emile | 0.79167 | 0.83333 | 0.041667 | Started planning the interaction of elements in the Profile Management page: Adding allergies, selecting Preferences
2026-02-01 | Marc Urbano | 0.79167 | 0.875 | 0.083333 | Worked on login.css
2026-02-02 | Martin Miskovski | 0.79167 | 0.91667 | 0.125 | Worked on css, added an error message for wrong given inputs by the user
2026-02-02 | Ethan Elkaim | 0.91667 | 0.97917 | 0.0625 | Tested out registration flow to ensure everything worked well. Fixed a few typos and some css
2026-02-03 | Chrisjan Alejandro | 0.64583 | 0.77083 | 0.125 | Integrated backend routes with the frontend profile management page. Configured server.js to handle preference update requests
2026-02-03 | Marc Urbano | 0.64583 | 0.72917 | 0.083333 | Finished login.css. Added background image for login UI. Created Pull Request.
2026-02-04 | Chrisjan Alejandro | 0.72917 | 0.77083 | 0.041667 | Finalized profile management backend.Verified data persistence and completed error handling for user updates.
2026-02-04 | Kepler Paul-Emile | 0.79167 | 0.91667 | 0.125 | Finalized the look of the profile management page
2026-02-05 | Kadio Paul-Philippe Ehui | 0.79167 | 0.89583 | 0.10417 | Miscellaneous debugging and testing
2026-02-05 | Ethan Elkaim | 0.5 | 0.54167 | 0.041667 | Auth UI polish + styling error messages